## Weekly Report
Date | Weekday | Pratik | Khushi | Praneeta | Shreya
2026-03-21 | Saturday | Worked on fixing pod restarting every hour | Worked on training models and experimenting with different YOLO variants | Absent | Worked on two frames (Zoomed-track)
2026-03-22 | Sunday | Holiday | Leave | Holiday | Holiday
2026-03-23 | Monday | Self-tested trained YOLOv9m model on non-drone dataset | Continued training models and exploring different YOLO architectures | Found YOLO NAS model, setup python in pod, faced dependency issues | Continued working on two frames
2026-03-24 | Tuesday | Tested YOLOv9m model on indoor dataset | Reviewed videos/resources for optimization techniques | Resolving dependency errors due to Super Gradients | Worked on frame parameters (coordinates & target center)
2026-03-25 | Wednesday | Day and night IR data collection via Trakka (drone & non-drone) | Studied approaches to improve model accuracy | Tried resolving dependency issues | Integrated all tasks into one code
2026-03-26 | Thursday | Tested YOLOv9m model outdoor, prepared additional dataset | Extracted frames from videos for dataset | Absent | Released EXE for testing and conducted field testing
2026-03-27 | Friday | Transferred training dataset to cluster, researched model performance improvement | Started annotating extracted frames | Resolved dependency errors in pod | Reading Trakka docs and working on tracking integration